## Slide 1
AGILE
TRANSFORMATION PLAN
Reporting & Analytics | Commercial & Finance
From Zero to Agile — A Phased Roadmap
Prepared by: Agile Transformation Office | April 2025

## Slide 2
Agenda
01
Current State Assessment
Where both teams stand today
02
Agile Transformation Goals
What success looks like
03
Team-Specific Strategies
R&A and C&F tailored plans
04
3-Phase Rollout Plan
Foundation → Adoption → Optimization
05
Training Curriculum
Workshops, coaching, and ceremonies
06
Key Ceremonies by Team
Sprint, Kanban, and hybrid approach
07
Success Metrics
How we measure progress
08
Risks & Mitigations
What to watch for
09
Next Steps
Actions starting this week

## Slide 3
Current State Assessment
Team: Reporting & Analytics (R&A)
Uses ServiceNow for support, enhancements & projects
No story grooming or backlog management
No sprint planning, review, or retrospective
Daily stand-up only — no structured cadence
Work items not sized or prioritized by team
No definition of 'Done' established
Reactive work culture; little predictability
Maturity: Level 0–1
Team: Commercial & Finance (C&F)
2 interns/co-ops active for 6-month rotation
Currently scoping epics & user stories (new!)
First backlog grooming session Monday
No sprint ceremonies established yet
Team learning Agile/Scrum basics now
No velocity or capacity baselines
Opportunity: greenfield Agile adoption
Maturity: Level 0–1

## Slide 4
Transformation Goals — What Success Looks Like
🎯
Predictable Delivery
Teams commit to sprint goals and deliver consistently with measurable velocity.
🔄
Living Backlog
Prioritized, groomed backlogs that reflect current business value at all times.
📣
Transparency
Work is visible to stakeholders; blockers surface quickly in daily stand-up.
🤝
Collaborative Culture
Teams own their process, run retrospectives, and self-improve each sprint.
📈
Continuous Improvement
Measurable increase in Agile maturity score every quarter using team surveys.
⚡
Faster Value Delivery
Shorten time-to-production through iterative delivery and CI/CD awareness.

## Slide 5
3-Phase Transformation Roadmap
PHASE 01
FOUNDATION
Weeks 1–4
Agile 101 Workshop
Scrum roles defined
Backlog creation
First ceremonies kick off
ServiceNow alignment (R&A)
PHASE 02
ADOPTION
Weeks 5–12
2-week sprint cadence
Grooming, Planning, Review, Retro
Story point estimation
Kanban for R&A ongoing work
Velocity tracking begins
PHASE 03
OPTIMIZATION
Weeks 13–24
Definition of Done matured
Metrics & dashboards live
Coaching reduced; team self-serve
Agile maturity assessment
SAFe concepts introduced
▶
▶

## Slide 6
Phase 1: Foundation (Weeks 1–4)
Build shared understanding, define roles, and launch the first ceremonies.
Week 1: Agile 101 Training
✓ Half-day Agile/Scrum workshop (both teams)
✓ Define Scrum roles: PO, SM, Dev Team
✓ Explain ceremonies: why & how
✓ Intro to user stories & acceptance criteria
Week 2: Backlog Bootstrap
✓ R&A: Map ServiceNow ticket types to Agile backlog
✓ C&F: Validate epics & user stories in progress
✓ Both teams: create initial product backlog
✓ Prioritize top 20 stories together
Week 3: First Sprint Planning
✓ C&F: Run Sprint 0 planning session
✓ R&A: Set up Kanban board in ServiceNow
✓ Estimate stories with T-shirt sizing or SP
✓ Agree on Sprint Goal format
Week 4: Launch Ceremonies
✓ First stand-up retooled with Agile format
✓ C&F: Sprint 1 begins
✓ R&A: Kanban WIP limits established
✓ Retrospective template introduced

## Slide 7
Phase 2: Adoption (Weeks 5–12)
Embed ceremonies, start measuring velocity, and stabilize the cadence.
C&F — Full Scrum Cadence
2-week sprints
Commit to 10-day cycle; timebox strictly
Backlog Grooming
Weekly 60-min session; refine & size top stories
Sprint Planning
Bi-weekly; select stories, set sprint goal
Daily Stand-up
15 min; yesterday / today / blockers
Sprint Review
Demo to stakeholders; gather feedback
Sprint Retrospective
What went well / what to improve
Velocity Tracking
Chart story points per sprint; set capacity baseline
Intern Pairing
Senior + intern on stories; knowledge transfer
R&A — Kanban + Scrum Hybrid
Kanban Board
ServiceNow: To Do / In Progress / In Review / Done
WIP Limits
Cap concurrent items; reduce context switching
Weekly Grooming
Review new tickets; add acceptance criteria
Stand-up Retool
Walk the board right-to-left; focus on flow
Swim Lanes
Support / Enhancement / Project work separated
2-Week Cadence Reviews
Bi-weekly demo of completed enhancements
Retrospective
Bi-weekly; inspect & adapt process
Metrics: Lead/Cycle Time
Track & report flow metrics monthly

## Slide 8
Phase 3: Optimization (Weeks 13–24)
Mature practices, reduce coaching dependency, and prepare for scaled agile.
Definition of Done (DoD)
→ Both teams formalize DoD checklist
→ DoD reviewed & updated each quarter
→ Linked to quality gates in ServiceNow
Metrics & Dashboards
→ Velocity chart live for C&F
→ Lead/Cycle time dashboard for R&A
→ Agile maturity scorecard shared monthly
Coaching Wind-Down
→ Scrum Master transitions to servant leader
→ Teams run ceremonies independently
→ Monthly drop-in coaching sessions remain
SAFe Introduction
→ Intro to PI Planning structure
→ Team-level ART awareness session
→ Explore Portfolio Kanban for R&A projects
Agile Maturity Assessment
→ Baseline survey at start of Phase 3
→ Team self-assessment each sprint
→ Target: reach Level 3 by end of Phase 3
Continuous Improvement
→ Retrospective actions tracked to completion
→ Innovation spikes: 10% capacity per sprint
→ Communities of practice established

## Slide 9
Training Curriculum
Module
Topics Covered
Format
Duration
Audience
Agile Foundations
Agile Manifesto, 12 principles, Scrum vs Kanban vs SAFe
Workshop
4 hrs
Both Teams
Scrum Ceremonies
Stand-up, Planning, Review, Retro — purpose, format, tips
Workshop
3 hrs
C&F + R&A
User Story Writing
INVEST criteria, acceptance criteria, story maps, epics
Workshop
2 hrs
Both Teams
Estimation Techniques
Story points, T-shirt sizing, planning poker, affinity mapping
Workshop
2 hrs
Both Teams
Kanban for ServiceNow
Board setup, WIP limits, swim lanes, flow metrics
Hands-On
2 hrs
R&A Only
Backlog Management
Prioritization (MoSCoW, WSJF), grooming techniques, PO role
Workshop
2 hrs
Both Teams
Agile Metrics
Velocity, burndown, lead/cycle time, team health checks
Lecture
1.5 hrs
Both Teams
Scrum Master Coaching
Facilitation, servant leadership, removing blockers
1:1 Coaching
Ongoing
Scrum Masters
SAFe Awareness
PI Planning intro, ART concept, value streams (Phase 3)
Seminar
3 hrs
Both Teams

## Slide 10
Key Ceremonies by Team — Sprint Cadence View
2-Week Sprint (C&F Scrum) | 2-Week Cycle (R&A Kanban)
Mon
Tue
Wed
Thu
Fri
Mon
Tue
Wed
Thu
Fri
Week 1
Week 2
C&F
(Scrum)
Sprint
Planning
Stand-up
Stand-up
+Grooming
Stand-up
Stand-up
Stand-up
Stand-up
+Grooming
Stand-up
Sprint
Review
Retro
R&A
(Kanban)
Stand-up
(Board)
Stand-up
(Board)
Stand-up
+Grooming
Stand-up
(Board)
Stand-up
(Board)
Stand-up
(Board)
Stand-up
(Board)
Cycle
Review
Retro
Stand-up
(Board)
Legend:
Planning
Daily Stand-up
Review/Demo
Retrospective
Grooming

## Slide 11
Team R&A — ServiceNow Agile Strategy
Recommendation: Kanban-first with bi-weekly cadence ceremonies — meets the team where they are.
Kanban Board Structure (ServiceNow)
Backlog
#100
#101
#102
To Do
WIP: 5
#103
#104
#105
In Progress
WIP: 3
#106
#107
#108
In Review
WIP: 2
#109
#110
#111
Done
#112
Key Practices & Guardrails
Swim Lane Separation
Support tickets separate from Enhancement / Project stories — prevents cross-contamination of priorities
WIP Limits
Hard caps (3 In Progress) force focus and surface blockers before they become crises
Story Acceptance Criteria
Every ServiceNow ticket must have clear 'done' condition before moving to In Progress
Weekly Ticket Grooming
60 min each week: triage new tickets, write AC, estimate effort using S/M/L
Bi-Weekly Cadence Review
Show completed enhancements to stakeholders; capture feedback before starting new work
Flow Metrics
Track lead time & cycle time in ServiceNow reports; share monthly with team & leadership

## Slide 12
Team C&F — Scrum Strategy & Intern Integration
Scrum by the book — leverage the interns' fresh perspective as a forcing function for adoption.
Product
Backlog
→
Sprint
Planning
→
Sprint
Backlog
→
Daily
Scrum
→
Sprint
Increment
Retro →
Intern/Co-op Integration
• Interns own stories from grooming through demo
• Pair each intern with a senior team member
• Interns rotate as Scrum Master after Sprint 3
• 6-month rotation = 12+ sprints of experience
• End-of-rotation retrospective & handoff doc
Scrum Roles (C&F)
• Product Owner: Business lead defines priorities
• Scrum Master: Agile coach facilitates (Phase 1-2)
• Dev Team: Full team incl. interns self-organizes
• Stakeholders attend Sprint Review (not retro)
• SM transitions to team member in Phase 3
Story & Acceptance Criteria Standards
• Format: As a [user], I want [goal], so that [benefit]
• INVEST criteria applied to all stories
• Minimum 2 acceptance criteria per story
• Story size: ideally ≤ 3 story points to stay in 1 sprint
• Epics have clear business value statement
Definition of Done (Initial)
• Code reviewed by at least 1 team member
• Acceptance criteria all passing
• Documentation updated (if applicable)
• Demo-ready at Sprint Review
• No known P1/P2 bugs outstanding

## Slide 13
Success Metrics — How We Measure Progress
Agile Maturity
Metric
Description
Cadence
Target
Maturity Score
Team self-assessment survey (1–5 scale)
Quarterly
Level 1 → Level 3 by Month 6
Ceremony Adoption
% of ceremonies run on schedule
Weekly
100% by end of Phase 2
C&F Scrum
Metric
Description
Cadence
Target
Velocity
Story points completed per sprint
Per Sprint
Stable ± 10% by Sprint 6
Sprint Goal Hit Rate
% of sprints where goal is met
Per Sprint
≥ 80% by Sprint 4
Backlog Hygiene
% groomed stories in top of backlog
Weekly
≥ 80% ready at all times
R&A Kanban
Metric
Description
Cadence
Target
Lead Time
Avg days from ticket creation to Done
Monthly
20% reduction by Month 4
Cycle Time
Avg days from In Progress to Done
Monthly
15% reduction by Month 4
WIP Compliance
% of days WIP limits respected
Weekly
≥ 90% compliance
Team Health
Metric
Description
Cadence
Target
Retro Action Rate
% retro actions completed next sprint
Per Sprint
≥ 75% completion rate
Blocker Resolution
Avg hours to resolve stand-up blocker
Weekly
< 24 hrs by Phase 3
Team Satisfaction
Anonymous pulse survey (1–5)
Monthly
Average ≥ 4.0

## Slide 14
Risks & Mitigations
Risk
Likelihood
Impact
Mitigation Strategy
Resistance to Change
High
High
Secure leadership sponsorship early; frame Agile as removing pain, not adding process. Use quick wins in Sprint 1 to build momentum.
Ceremony Fatigue
Medium
Medium
Keep all ceremonies timeboxed strictly. Retrospectively adjust length if teams signal fatigue. Show ROI via metrics dashboard.
Intern Turnover (C&F)
High
Medium
Document everything. Use Definition of Done to enforce knowledge capture. Overlap periods between intern rotations.
ServiceNow Constraints (R&A)
Medium
High
Audit ServiceNow Kanban features early in Phase 1. Identify gaps and supplement with a visual board (physical or Miro) if needed.
No Dedicated Scrum Master
High
High
Coach assigns a volunteer SM per team. SM duties rotate in Phase 3 to spread skills and reduce single-point-of-failure.
Backlog Prioritization Gaps
Medium
High
PO training is mandatory in Phase 1. Use MoSCoW or WSJF frameworks. Escalation path defined for prioritization conflicts.

## Slide 15
Next Steps — Actions Starting This Week
This Week
1. Confirm Scrum Master / Agile Coach assignment for both teams
2. C&F: Run first backlog grooming session Monday (already scheduled)
3. R&A: Audit ServiceNow board — identify Kanban configuration gaps
4. Schedule Agile 101 Workshop for both teams (target: end of Week 1)
Week 2
1. Both teams: Complete initial backlog creation with top 20 stories
2. C&F: Assign Product Owner; confirm sprint length (2 weeks)
3. R&A: Define swim lanes and WIP limits in ServiceNow
4. Set up agile maturity baseline survey (all team members)
Week 3–4
1. C&F: Run Sprint 0 planning; begin Sprint 1
2. R&A: First stand-up in new Kanban walk-the-board format
3. Both teams: Introduce retrospective — first session end of Week 4
4. Coach: Schedule bi-weekly check-ins with both teams
Monthly
1. Review Agile maturity scores and adjust coaching intensity
2. Stakeholder update: share metrics dashboard and sprint demos
3. Retrospective health check: are actions being completed?
4. Evaluate readiness to progress from Phase 1 → Phase 2

## Slide 16
The journey to Agile maturity
starts with a
single ceremony.
Questions & Discussion
Agile Transformation Office | Ready to Start Monday